WEOBLEY PARISH NEIGHBOURHOOD PLAN - PROJECT TIMELINE

| Agreement by Parish Council to go forward with NDP | May 2013 |
| --- | --- |
| Formal approval of NDP Area . | August 2013 |
| Steering Group appointed to begin the NDP process. | September 2013 |
| NDP progress halted following receipt of planning applications for 15 houses on land east of the Primary School and 40 houses on land in Gadbridge Road |  |
| Parish Council agreement to resume NDP process | May 2014 |
| Strategic Environmental Assessment completed by Herefordshire Council | September 2014 |
| Community consultation and ‘Planning for Real’ event | April - September 2015 |
| Community Survey | February - March 2016 |
| Survey results published | April 2016 |
| Draft ‘Vision’ & ‘Objectives’ | November 2016 |
| Site Assessments | February 2017 |
| Draft Policy options Public Consultation - Vision & Objectives and Policy options | April - May 2017 |
| Preparation of 1st draft of Plan document in consultation with Planning Consultant | August 2017 – February 2018 |
| Presentation to Parish Council for formal adoption of 1st Draft Plan | March 2018 |
| Submission of 1st Draft for SEA & HA Assessment | April 2018 |
| Regulation 14 Draft Plan Consultation and Formal Representation | June- August 2018 |
| Preparation of Basic Condition Statement | August – September 2018 |
| 2nd draft of Plan document prepared |  |
| Presentation to Parish Council for formal adoption of 2nd Draft Plan | September 2018 |
| Submission of 2nd Draft for SEA & HA Assessments | September – October 2018 |
| Preparation of Consultation Statement - | December2018 – January 2019 |
| Plan forwarded to Local Authority under Regulation 15 | January 2019 |
| Regulation 16 – 6 week Consultation | January – March 2019 |
| Independent Examination and modification | May – June 2019 |
| Final Draft of Plan and SEA & HA Assessments | July 2019 |
| Referendum and Final Plan adopted | September 2019 |